## Sheet1
|  |  | 2023-03-01 |  |  |  |  | 2023-04-01 |  |  |  |  | 2023-05-01 |  |  |  |  | 2023-06-01
ID | Task Name | Deliverables | 1.3 | 8.3 | 15.3 | 22.3 | 29.3 | 1.4 | 8.4 | 15.4 | 22.4 | 29.4 | 1.5 | 8.5 | 15.5 | 22.5 | 29.5 | 1.6
WP 1 | Domain Review
WP 1.1 | Introduction | Task 1 - Rewritten Description
WP 1.2 | Research and Semester Plan | Presentation of Semster Plan
WP 1.3 | Finishing Machine Learning Course CNN | Summary / Progress Reports
WP 1.4 | Data Set Collection | Data Set Summary and Report
WP 2 | Development of Application
WP 2.1 | Developing Application Block Diagram / Workflow | Diagram Report
WP 2.2 | Implementation of application | Progress Reports
WP 2.3 | Testing and Validation of application | Progress Reports
WP 3 | Application Testing | Test Results
WP 3.1 | Enhancing
WP 3.2 | Debugging
WP 3.4 | Black box testing
WP 4 | Interim Reports
WP 4.1 | Interim Report 1
WP 4.2 | Interim Report 2
WP 5 | Thesis Finalization
WP 5.1 | Final Thesis Submission
WP 5.2 | Thesis Defense
WP 6 | Documentation And Thesis Composition
WP 6.1 | Thesis Template
WP 6.2 | Thesis Final Draft